## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
Innovation Program | AI/ML Cluster Upgrade v5 | IT | Distributed Tracing (Jaeger/OpenTelemetry) | Update | Business Analyst | IT | Business Analyst 1 | 17 | Requirements analysis; Process documentation; Stakeholder management
Innovation Program | AI/ML Cluster Upgrade v5 | IT | Distributed Tracing (Jaeger/OpenTelemetry) | Update | Software Engineer | IT | Software Engineer 1 | 16 | Technical implementation; Code development; Unit testing
Innovation Program | AI/ML Cluster Upgrade v5 | IT | Distributed Tracing (Jaeger/OpenTelemetry) | Update | Test Engineer | IT | Test Engineer 1 | 11 | Test planning; Test execution; Quality assurance
Innovation Program | AI/ML Cluster Upgrade v5 | IT | Distributed Tracing (Jaeger/OpenTelemetry) | Update | Solution Architect | IT | Solution Architect 1 | 12 | Architecture design; Technical guidance; Solution review
Innovation Program | AI/ML Cluster Upgrade v5 | IT | Security Management | Delete | Business Analyst | IT | Business Analyst 1 | 8 | Requirements analysis; Process documentation; Stakeholder management
Innovation Program | AI/ML Cluster Upgrade v5 | IT | Security Management | Delete | Software Engineer | IT | Software Engineer 1 | 11 | Technical implementation; Code development; Unit testing
Innovation Program | AI/ML Cluster Upgrade v5 | IT | Security Management | Delete | Test Engineer | IT | Test Engineer 1 | 7 | Test planning; Test execution; Quality assurance
Innovation Program | AI/ML Cluster Upgrade v5 | IT | Security Management | Delete | Solution Architect | IT | Solution Architect 1 | 7 | Architecture design; Technical guidance; Solution review
Innovation Program | AI/ML Cluster Upgrade v5 | BUSINESS | Fraud Detection | Create | Business Analyst | IT | Business Analyst 1 | 19 | Requirements analysis; Process documentation; Stakeholder management
Innovation Program | AI/ML Cluster Upgrade v5 | BUSINESS | Fraud Detection | Create | Software Engineer | IT | Software Engineer 1 | 35 | Technical implementation; Code development; Unit testing
Innovation Program | AI/ML Cluster Upgrade v5 | BUSINESS | Fraud Detection | Create | Test Engineer | IT | Test Engineer 1 | 27 | Test planning; Test execution; Quality assurance
Innovation Program | AI/ML Cluster Upgrade v5 | IT | IT Asset Management | Update | Business Analyst | IT | Business Analyst 1 | 15 | Requirements analysis; Process documentation; Stakeholder management
Innovation Program | AI/ML Cluster Upgrade v5 | IT | IT Asset Management | Update | Product Owner | IT | Product Owner 1 | 10 | Backlog management; Feature prioritization; Value assessment
Innovation Program | AI/ML Cluster Upgrade v5 | IT | IT Asset Management | Update | Software Engineer | IT | Software Engineer 1 | 20 | Technical implementation; Code development; Unit testing
Innovation Program | AI/ML Cluster Upgrade v5 | IT | IT Asset Management | Update | Test Engineer | IT | Test Engineer 1 | 17 | Test planning; Test execution; Quality assurance
Innovation Program | AI/ML Cluster Upgrade v5 | IT | IT Asset Management | Update | Solution Architect | IT | Solution Architect 1 | 9 | Architecture design; Technical guidance; Solution review
Innovation Program | AI/ML Cluster Upgrade v5 | IT | IT Asset Management | Update | Solution Architect | IT | Solution Architect 2 | 17 | Architecture design; Technical guidance; Solution review
Innovation Program | AI/ML Cluster Upgrade v5 | IT | IT Asset Management | Update | Platform Engineer | IT | Platform Engineer 1 | 12 | Platform development; Infrastructure setup; Platform maintenance
Innovation Program | AI/ML Cluster Upgrade v5 | IT | IT Asset Management | Update | Site Reliability Engineer | IT | Site Reliability Engineer 1 | 11 | Reliability monitoring; Performance optimization; Incident response
Innovation Program | AI/ML Cluster Upgrade v5 | IT | IT Asset Management | Update | Security Engineer | IT | Security Engineer 1 | 12 | Security implementation; Security testing; Security monitoring