## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
Digital Program | API Cluster Implementation v11 | IT | API Gateway (Envoy/Contour) | Create | Business Analyst | IT | Business Analyst 1 | 17 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Implementation v11 | IT | API Gateway (Envoy/Contour) | Create | Product Owner | IT | Product Owner 1 | 15 | Backlog management; Feature prioritization; Value assessment
Digital Program | API Cluster Implementation v11 | IT | API Gateway (Envoy/Contour) | Create | Business Process Expert | IT | Business Process Expert 1 | 13 | Process optimization; Business rules definition; Process implementation
Digital Program | API Cluster Implementation v11 | IT | API Gateway (Envoy/Contour) | Create | Software Engineer | IT | Software Engineer 1 | 33 | Technical implementation; Code development; Unit testing
Digital Program | API Cluster Implementation v11 | IT | API Gateway (Envoy/Contour) | Create | Test Engineer | IT | Test Engineer 1 | 24 | Test planning; Test execution; Quality assurance
Digital Program | API Cluster Implementation v11 | IT | API Gateway (Envoy/Contour) | Create | Solution Architect | IT | Solution Architect 1 | 19 | Architecture design; Technical guidance; Solution review
Digital Program | API Cluster Implementation v11 | IT | API Gateway (Envoy/Contour) | Create | Platform Engineer | IT | Platform Engineer 1 | 25 | Platform development; Infrastructure setup; Platform maintenance
Digital Program | API Cluster Implementation v11 | IT | API Gateway (Envoy/Contour) | Create | Site Reliability Engineer | IT | Site Reliability Engineer 1 | 17 | Reliability monitoring; Performance optimization; Incident response
Digital Program | API Cluster Implementation v11 | BUSINESS | Account Management | Delete | Business Analyst | IT | Business Analyst 1 | 5 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Implementation v11 | BUSINESS | Account Management | Delete | Software Engineer | IT | Software Engineer 1 | 7 | Technical implementation; Code development; Unit testing
Digital Program | API Cluster Implementation v11 | BUSINESS | Account Management | Delete | Test Engineer | IT | Test Engineer 1 | 8 | Test planning; Test execution; Quality assurance
Digital Program | API Cluster Implementation v11 | BUSINESS | Account Management | Delete | Solution Architect | IT | Solution Architect 1 | 6 | Architecture design; Technical guidance; Solution review
Digital Program | API Cluster Implementation v11 | BUSINESS | Account Management | Delete | Platform Engineer | IT | Platform Engineer 1 | 9 | Platform development; Infrastructure setup; Platform maintenance
Digital Program | API Cluster Implementation v11 | IT | Cloud Native CI/CD (Tekton/Spinnaker) | Update | Business Analyst | IT | Business Analyst 1 | 15 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Implementation v11 | IT | Cloud Native CI/CD (Tekton/Spinnaker) | Update | Product Owner | IT | Product Owner 1 | 7 | Backlog management; Feature prioritization; Value assessment
Digital Program | API Cluster Implementation v11 | IT | Cloud Native CI/CD (Tekton/Spinnaker) | Update | Business Process Expert | IT | Business Process Expert 1 | 11 | Process optimization; Business rules definition; Process implementation
Digital Program | API Cluster Implementation v11 | IT | Cloud Native CI/CD (Tekton/Spinnaker) | Update | Software Engineer | IT | Software Engineer 1 | 19 | Technical implementation; Code development; Unit testing
Digital Program | API Cluster Implementation v11 | IT | Cloud Native CI/CD (Tekton/Spinnaker) | Update | Test Engineer | IT | Test Engineer 1 | 15 | Test planning; Test execution; Quality assurance
Digital Program | API Cluster Implementation v11 | IT | Cloud Native CI/CD (Tekton/Spinnaker) | Update | Solution Architect | IT | Solution Architect 1 | 15 | Architecture design; Technical guidance; Solution review
Digital Program | API Cluster Implementation v11 | IT | Cloud Native CI/CD (Tekton/Spinnaker) | Update | Platform Engineer | IT | Platform Engineer 1 | 18 | Platform development; Infrastructure setup; Platform maintenance
Digital Program | API Cluster Implementation v11 | IT | Cloud Native CI/CD (Tekton/Spinnaker) | Update | Site Reliability Engineer | IT | Site Reliability Engineer 1 | 10 | Reliability monitoring; Performance optimization; Incident response
Digital Program | API Cluster Implementation v11 | IT | Cloud Native CI/CD (Tekton/Spinnaker) | Update | Site Reliability Engineer | IT | Site Reliability Engineer 2 | 13 | Reliability monitoring; Performance optimization; Incident response
Digital Program | API Cluster Implementation v11 | IT | Cloud Native CI/CD (Tekton/Spinnaker) | Update | Security Engineer | IT | Security Engineer 1 | 18 | Security implementation; Security testing; Security monitoring
Digital Program | API Cluster Implementation v11 | IT | Cloud Native CI/CD (Tekton/Spinnaker) | Update | Security Engineer | IT | Security Engineer 2 | 16 | Security implementation; Security testing; Security monitoring