## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
Digital Program | API Cluster Implementation v14 | BUSINESS | Account Management | Delete | Business Analyst | IT | Business Analyst 1 | 6 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Implementation v14 | BUSINESS | Trade Settlement | Create | Business Analyst | IT | Business Analyst 1 | 23 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Implementation v14 | BUSINESS | Trade Settlement | Create | Software Engineer | IT | Software Engineer 1 | 20 | Technical implementation; Code development; Unit testing
Digital Program | API Cluster Implementation v14 | BUSINESS | Customer Agreement | Update | Business Analyst | IT | Business Analyst 1 | 15 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Implementation v14 | BUSINESS | Customer Agreement | Update | Software Engineer | IT | Software Engineer 1 | 23 | Technical implementation; Code development; Unit testing
Digital Program | API Cluster Implementation v14 | BUSINESS | Collateral Management | Update | Business Analyst | IT | Business Analyst 1 | 12 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Implementation v14 | BUSINESS | Market Research | Update | Business Analyst | IT | Business Analyst 1 | 16 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Implementation v14 | BUSINESS | Product Pricing | Update | Business Analyst | IT | Business Analyst 1 | 12 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Implementation v14 | IT | Package Management (Helm/Brigade) | Delete | Business Analyst | IT | Business Analyst 1 | 6 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Implementation v14 | BUSINESS | Regulatory Compliance | Delete | Business Analyst | IT | Business Analyst 1 | 6 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Implementation v14 | BUSINESS | Regulatory Compliance | Delete | Software Engineer | IT | Software Engineer 1 | 9 | Technical implementation; Code development; Unit testing
Digital Program | API Cluster Implementation v14 | BUSINESS | Wealth Management | Delete | Business Analyst | IT | Business Analyst 1 | 8 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Implementation v14 | BUSINESS | Channel Management | Update | Business Analyst | IT | Business Analyst 1 | 18 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Implementation v14 | BUSINESS | Channel Management | Update | Software Engineer | IT | Software Engineer 1 | 18 | Technical implementation; Code development; Unit testing
Digital Program | API Cluster Implementation v14 | BUSINESS | Sales Product Matching | Delete | Business Analyst | IT | Business Analyst 1 | 4 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Implementation v14 | BUSINESS | Loan Processing | Update | Business Analyst | IT | Business Analyst 1 | 14 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Implementation v14 | BUSINESS | Loan Processing | Update | Software Engineer | IT | Software Engineer 1 | 12 | Technical implementation; Code development; Unit testing
Digital Program | API Cluster Implementation v14 | BUSINESS | Customer Onboarding | Update | Business Analyst | IT | Business Analyst 1 | 12 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Implementation v14 | BUSINESS | Fraud Detection | Delete | Business Analyst | IT | Business Analyst 1 | 8 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Implementation v14 | BUSINESS | Fraud Detection | Delete | Software Engineer | IT | Software Engineer 1 | 9 | Technical implementation; Code development; Unit testing