## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
Digital Program | API Cluster Migration v12 | BUSINESS | Payment Execution | Update | Business Analyst | IT | Business Analyst 1 | 15 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Migration v12 | BUSINESS | Payment Execution | Update | Software Engineer | IT | Software Engineer 1 | 22 | Technical implementation; Code development; Unit testing
Digital Program | API Cluster Migration v12 | BUSINESS | Customer Onboarding | Create | Business Analyst | IT | Business Analyst 1 | 18 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Migration v12 | BUSINESS | Customer Onboarding | Create | Software Engineer | IT | Software Engineer 1 | 35 | Technical implementation; Code development; Unit testing
Digital Program | API Cluster Migration v12 | BUSINESS | Wealth Management | Create | Business Analyst | IT | Business Analyst 1 | 28 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Migration v12 | BUSINESS | Wealth Management | Create | Software Engineer | IT | Software Engineer 1 | 34 | Technical implementation; Code development; Unit testing
Digital Program | API Cluster Migration v12 | BUSINESS | Market Research | Delete | Business Analyst | IT | Business Analyst 1 | 7 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Migration v12 | BUSINESS | Market Research | Delete | Software Engineer | IT | Software Engineer 1 | 7 | Technical implementation; Code development; Unit testing
Digital Program | API Cluster Migration v12 | IT | Security Policy Enforcement (OPA/Falco) | Delete | Business Analyst | IT | Business Analyst 1 | 5 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Migration v12 | IT | Security Policy Enforcement (OPA/Falco) | Delete | Software Engineer | IT | Software Engineer 1 | 7 | Technical implementation; Code development; Unit testing
Digital Program | API Cluster Migration v12 | BUSINESS | Channel Management | Update | Business Analyst | IT | Business Analyst 1 | 15 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Migration v12 | BUSINESS | Card Authorization | Delete | Business Analyst | IT | Business Analyst 1 | 5 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Migration v12 | BUSINESS | Card Authorization | Delete | Software Engineer | IT | Software Engineer 1 | 7 | Technical implementation; Code development; Unit testing
Digital Program | API Cluster Migration v12 | BUSINESS | Customer Identity Management | Create | Business Analyst | IT | Business Analyst 1 | 26 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Migration v12 | BUSINESS | Risk Management | Create | Business Analyst | IT | Business Analyst 1 | 30 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Migration v12 | IT | Distributed Tracing (Jaeger/OpenTelemetry) | Update | Business Analyst | IT | Business Analyst 1 | 15 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Migration v12 | IT | Distributed Tracing (Jaeger/OpenTelemetry) | Update | Software Engineer | IT | Software Engineer 1 | 20 | Technical implementation; Code development; Unit testing
Digital Program | API Cluster Migration v12 | BUSINESS | Investment Portfolio Management | Update | Business Analyst | IT | Business Analyst 1 | 17 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Migration v12 | BUSINESS | Investment Portfolio Management | Update | Software Engineer | IT | Software Engineer 1 | 21 | Technical implementation; Code development; Unit testing
Digital Program | API Cluster Migration v12 | IT | Database Orchestration (Vitess/TiKV) | Create | Business Analyst | IT | Business Analyst 1 | 24 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Migration v12 | BUSINESS | Sales Product Matching | Update | Business Analyst | IT | Business Analyst 1 | 12 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Cluster Migration v12 | BUSINESS | Financial Accounting | Delete | Business Analyst | IT | Business Analyst 1 | 9 | Requirements analysis; Process documentation; Stakeholder management