## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
Digital Program | API Platform Migration v3 | BUSINESS | Payment Execution | Delete | Business Analyst | IT | Business Analyst 1 | 5 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Platform Migration v3 | BUSINESS | Payment Execution | Delete | Product Owner | IT | Product Owner 1 | 5 | Backlog management; Feature prioritization; Value assessment
Digital Program | API Platform Migration v3 | BUSINESS | Payment Execution | Delete | Business Process Expert | IT | Business Process Expert 1 | 6 | Process optimization; Business rules definition; Process implementation
Digital Program | API Platform Migration v3 | BUSINESS | Payment Execution | Delete | Software Engineer | IT | Software Engineer 1 | 9 | Technical implementation; Code development; Unit testing
Digital Program | API Platform Migration v3 | BUSINESS | Payment Execution | Delete | Test Engineer | IT | Test Engineer 1 | 7 | Test planning; Test execution; Quality assurance
Digital Program | API Platform Migration v3 | BUSINESS | Payment Execution | Delete | Solution Architect | IT | Solution Architect 1 | 6 | Architecture design; Technical guidance; Solution review
Digital Program | API Platform Migration v3 | BUSINESS | Payment Execution | Delete | Platform Engineer | IT | Platform Engineer 1 | 10 | Platform development; Infrastructure setup; Platform maintenance
Digital Program | API Platform Migration v3 | BUSINESS | Payment Execution | Delete | Site Reliability Engineer | IT | Site Reliability Engineer 1 | 6 | Reliability monitoring; Performance optimization; Incident response
Digital Program | API Platform Migration v3 | BUSINESS | Customer Identity Management | Create | Business Analyst | IT | Business Analyst 1 | 15 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Platform Migration v3 | BUSINESS | Customer Identity Management | Create | Product Owner | IT | Product Owner 1 | 17 | Backlog management; Feature prioritization; Value assessment
Digital Program | API Platform Migration v3 | BUSINESS | Customer Identity Management | Create | Software Engineer | IT | Software Engineer 1 | 25 | Technical implementation; Code development; Unit testing
Digital Program | API Platform Migration v3 | BUSINESS | Customer Identity Management | Create | Test Engineer | IT | Test Engineer 1 | 20 | Test planning; Test execution; Quality assurance
Digital Program | API Platform Migration v3 | BUSINESS | Customer Identity Management | Create | Solution Architect | IT | Solution Architect 1 | 26 | Architecture design; Technical guidance; Solution review
Digital Program | API Platform Migration v3 | BUSINESS | Customer Identity Management | Create | Platform Engineer | IT | Platform Engineer 1 | 28 | Platform development; Infrastructure setup; Platform maintenance
Digital Program | API Platform Migration v3 | IT | Package Management (Helm/Brigade) | Delete | Business Analyst | IT | Business Analyst 1 | 9 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Platform Migration v3 | IT | Package Management (Helm/Brigade) | Delete | Product Owner | IT | Product Owner 1 | 3 | Backlog management; Feature prioritization; Value assessment
Digital Program | API Platform Migration v3 | IT | Package Management (Helm/Brigade) | Delete | Software Engineer | IT | Software Engineer 1 | 7 | Technical implementation; Code development; Unit testing
Digital Program | API Platform Migration v3 | IT | Package Management (Helm/Brigade) | Delete | Test Engineer | IT | Test Engineer 1 | 5 | Test planning; Test execution; Quality assurance
Digital Program | API Platform Migration v3 | IT | Package Management (Helm/Brigade) | Delete | Solution Architect | IT | Solution Architect 1 | 6 | Architecture design; Technical guidance; Solution review
Digital Program | API Platform Migration v3 | IT | Package Management (Helm/Brigade) | Delete | Platform Engineer | IT | Platform Engineer 1 | 7 | Platform development; Infrastructure setup; Platform maintenance
Digital Program | API Platform Migration v3 | IT | Package Management (Helm/Brigade) | Delete | Site Reliability Engineer | IT | Site Reliability Engineer 1 | 7 | Reliability monitoring; Performance optimization; Incident response
Digital Program | API Platform Migration v3 | IT | Secret Management (Vault/Secrets Store CSI) | Delete | Business Analyst | IT | Business Analyst 1 | 5 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API Platform Migration v3 | IT | Secret Management (Vault/Secrets Store CSI) | Delete | Software Engineer | IT | Software Engineer 1 | 7 | Technical implementation; Code development; Unit testing
Digital Program | API Platform Migration v3 | IT | Secret Management (Vault/Secrets Store CSI) | Delete | Test Engineer | IT | Test Engineer 1 | 5 | Test planning; Test execution; Quality assurance
Digital Program | API Platform Migration v3 | IT | Secret Management (Vault/Secrets Store CSI) | Delete | Solution Architect | IT | Solution Architect 1 | 7 | Architecture design; Technical guidance; Solution review