## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
Digital Program | API System Upgrade v1 | IT | Problem Management | Update | Business Analyst | IT | Business Analyst 1 | 10 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API System Upgrade v1 | BUSINESS | Trade Settlement | Create | Business Analyst | IT | Business Analyst 1 | 24 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API System Upgrade v1 | BUSINESS | Trade Settlement | Create | Software Engineer | IT | Software Engineer 1 | 26 | Technical implementation; Code development; Unit testing
Digital Program | API System Upgrade v1 | BUSINESS | Trade Settlement | Create | Test Engineer | IT | Test Engineer 1 | 16 | Test planning; Test execution; Quality assurance
Digital Program | API System Upgrade v1 | BUSINESS | Customer Identity Management | Create | Business Analyst | IT | Business Analyst 1 | 20 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API System Upgrade v1 | BUSINESS | Customer Identity Management | Create | Software Engineer | IT | Software Engineer 1 | 31 | Technical implementation; Code development; Unit testing
Digital Program | API System Upgrade v1 | BUSINESS | Sales Product Matching | Update | Business Analyst | IT | Business Analyst 1 | 12 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API System Upgrade v1 | BUSINESS | Sales Product Matching | Update | Software Engineer | IT | Software Engineer 1 | 18 | Technical implementation; Code development; Unit testing
Digital Program | API System Upgrade v1 | IT | Service Level Management | Delete | Business Analyst | IT | Business Analyst 1 | 4 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API System Upgrade v1 | IT | Service Level Management | Delete | Software Engineer | IT | Software Engineer 1 | 7 | Technical implementation; Code development; Unit testing
Digital Program | API System Upgrade v1 | IT | Service Level Management | Delete | Test Engineer | IT | Test Engineer 1 | 6 | Test planning; Test execution; Quality assurance
Digital Program | API System Upgrade v1 | BUSINESS | Payment Execution | Delete | Business Analyst | IT | Business Analyst 1 | 4 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API System Upgrade v1 | BUSINESS | Payment Execution | Delete | Software Engineer | IT | Software Engineer 1 | 9 | Technical implementation; Code development; Unit testing
Digital Program | API System Upgrade v1 | BUSINESS | Risk Management | Delete | Business Analyst | IT | Business Analyst 1 | 4 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API System Upgrade v1 | BUSINESS | Regulatory Compliance | Create | Business Analyst | IT | Business Analyst 1 | 20 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API System Upgrade v1 | IT | IT Continuity Management | Create | Business Analyst | IT | Business Analyst 1 | 29 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API System Upgrade v1 | IT | IT Continuity Management | Create | Software Engineer | IT | Software Engineer 1 | 23 | Technical implementation; Code development; Unit testing
Digital Program | API System Upgrade v1 | BUSINESS | Channel Management | Update | Business Analyst | IT | Business Analyst 1 | 12 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API System Upgrade v1 | BUSINESS | Channel Management | Update | Software Engineer | IT | Software Engineer 1 | 13 | Technical implementation; Code development; Unit testing
Digital Program | API System Upgrade v1 | BUSINESS | Wealth Management | Update | Business Analyst | IT | Business Analyst 1 | 17 | Requirements analysis; Process documentation; Stakeholder management