## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
Digital Program | API System Upgrade v4 | IT | Continuous Delivery (Argo/Flux) | Delete | Business Analyst | IT | Business Analyst 1 | 8 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API System Upgrade v4 | IT | Continuous Delivery (Argo/Flux) | Delete | Software Engineer | IT | Software Engineer 1 | 11 | Technical implementation; Code development; Unit testing
Digital Program | API System Upgrade v4 | IT | Continuous Delivery (Argo/Flux) | Delete | Test Engineer | IT | Test Engineer 1 | 9 | Test planning; Test execution; Quality assurance
Digital Program | API System Upgrade v4 | IT | API Gateway (Envoy/Contour) | Create | Business Analyst | IT | Business Analyst 1 | 19 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API System Upgrade v4 | IT | API Gateway (Envoy/Contour) | Create | Product Owner | IT | Product Owner 1 | 16 | Backlog management; Feature prioritization; Value assessment
Digital Program | API System Upgrade v4 | IT | API Gateway (Envoy/Contour) | Create | Software Engineer | IT | Software Engineer 1 | 40 | Technical implementation; Code development; Unit testing
Digital Program | API System Upgrade v4 | IT | API Gateway (Envoy/Contour) | Create | Test Engineer | IT | Test Engineer 1 | 20 | Test planning; Test execution; Quality assurance
Digital Program | API System Upgrade v4 | IT | API Gateway (Envoy/Contour) | Create | Solution Architect | IT | Solution Architect 1 | 21 | Architecture design; Technical guidance; Solution review
Digital Program | API System Upgrade v4 | IT | Problem Management | Update | Business Analyst | IT | Business Analyst 1 | 9 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API System Upgrade v4 | IT | Problem Management | Update | Software Engineer | IT | Software Engineer 1 | 13 | Technical implementation; Code development; Unit testing
Digital Program | API System Upgrade v4 | IT | Problem Management | Update | Test Engineer | IT | Test Engineer 1 | 17 | Test planning; Test execution; Quality assurance
Digital Program | API System Upgrade v4 | IT | Problem Management | Update | Solution Architect | IT | Solution Architect 1 | 9 | Architecture design; Technical guidance; Solution review
Digital Program | API System Upgrade v4 | IT | Workload Scheduling (KubeEdge/Volcano) | Create | Business Analyst | IT | Business Analyst 1 | 27 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API System Upgrade v4 | IT | Workload Scheduling (KubeEdge/Volcano) | Create | Software Engineer | IT | Software Engineer 1 | 34 | Technical implementation; Code development; Unit testing
Digital Program | API System Upgrade v4 | IT | Workload Scheduling (KubeEdge/Volcano) | Create | Test Engineer | IT | Test Engineer 1 | 29 | Test planning; Test execution; Quality assurance
Digital Program | API System Upgrade v4 | IT | Workload Scheduling (KubeEdge/Volcano) | Create | Solution Architect | IT | Solution Architect 1 | 22 | Architecture design; Technical guidance; Solution review
Digital Program | API System Upgrade v4 | IT | Workload Scheduling (KubeEdge/Volcano) | Create | Platform Engineer | IT | Platform Engineer 1 | 35 | Platform development; Infrastructure setup; Platform maintenance
Digital Program | API System Upgrade v4 | IT | DevOps Management | Delete | Business Analyst | IT | Business Analyst 1 | 5 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | API System Upgrade v4 | IT | DevOps Management | Delete | Software Engineer | IT | Software Engineer 1 | 9 | Technical implementation; Code development; Unit testing