## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
Data Program | BI Platform Migration v9 | BUSINESS | Market Research | Create | Business Analyst | IT | Business Analyst 1 | 19 | Requirements analysis; Process documentation; Stakeholder management
Data Program | BI Platform Migration v9 | IT | DevOps Management | Create | Business Analyst | IT | Business Analyst 1 | 26 | Requirements analysis; Process documentation; Stakeholder management
Data Program | BI Platform Migration v9 | BUSINESS | Customer Onboarding | Create | Business Analyst | IT | Business Analyst 1 | 30 | Requirements analysis; Process documentation; Stakeholder management
Data Program | BI Platform Migration v9 | BUSINESS | Card Authorization | Create | Business Analyst | IT | Business Analyst 1 | 25 | Requirements analysis; Process documentation; Stakeholder management
Data Program | BI Platform Migration v9 | BUSINESS | Fraud Detection | Create | Business Analyst | IT | Business Analyst 1 | 27 | Requirements analysis; Process documentation; Stakeholder management
Data Program | BI Platform Migration v9 | BUSINESS | Fraud Detection | Create | Software Engineer | IT | Software Engineer 1 | 35 | Technical implementation; Code development; Unit testing
Data Program | BI Platform Migration v9 | BUSINESS | Product Pricing | Update | Business Analyst | IT | Business Analyst 1 | 16 | Requirements analysis; Process documentation; Stakeholder management
Data Program | BI Platform Migration v9 | BUSINESS | Product Pricing | Update | Software Engineer | IT | Software Engineer 1 | 12 | Technical implementation; Code development; Unit testing
Data Program | BI Platform Migration v9 | IT | API Gateway (Envoy/Contour) | Delete | Business Analyst | IT | Business Analyst 1 | 7 | Requirements analysis; Process documentation; Stakeholder management
Data Program | BI Platform Migration v9 | IT | API Gateway (Envoy/Contour) | Delete | Software Engineer | IT | Software Engineer 1 | 6 | Technical implementation; Code development; Unit testing
Data Program | BI Platform Migration v9 | IT | Serverless Platform (Knative/OpenFaaS) | Create | Business Analyst | IT | Business Analyst 1 | 20 | Requirements analysis; Process documentation; Stakeholder management
Data Program | BI Platform Migration v9 | IT | Serverless Platform (Knative/OpenFaaS) | Create | Software Engineer | IT | Software Engineer 1 | 29 | Technical implementation; Code development; Unit testing
Data Program | BI Platform Migration v9 | IT | Serverless Platform (Knative/OpenFaaS) | Create | Test Engineer | IT | Test Engineer 1 | 27 | Test planning; Test execution; Quality assurance
Data Program | BI Platform Migration v9 | BUSINESS | Channel Management | Update | Business Analyst | IT | Business Analyst 1 | 10 | Requirements analysis; Process documentation; Stakeholder management
Data Program | BI Platform Migration v9 | BUSINESS | Payment Execution | Delete | Business Analyst | IT | Business Analyst 1 | 9 | Requirements analysis; Process documentation; Stakeholder management
Data Program | BI Platform Migration v9 | BUSINESS | Payment Execution | Delete | Software Engineer | IT | Software Engineer 1 | 10 | Technical implementation; Code development; Unit testing
Data Program | BI Platform Migration v9 | BUSINESS | Wealth Management | Delete | Business Analyst | IT | Business Analyst 1 | 5 | Requirements analysis; Process documentation; Stakeholder management
Data Program | BI Platform Migration v9 | BUSINESS | Sales Product Matching | Create | Business Analyst | IT | Business Analyst 1 | 15 | Requirements analysis; Process documentation; Stakeholder management