## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Product Pricing | Create | Business Analyst | IT | Business Analyst 1 | 22 | Requirements analysis; Process documentation; Stakeholder management
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Product Pricing | Create | Software Engineer | IT | Software Engineer 1 | 34 | Technical implementation; Code development; Unit testing
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Collateral Management | Update | Business Analyst | IT | Business Analyst 1 | 15 | Requirements analysis; Process documentation; Stakeholder management
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Collateral Management | Update | Software Engineer | IT | Software Engineer 1 | 21 | Technical implementation; Code development; Unit testing
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Sales Product Matching | Update | Business Analyst | IT | Business Analyst 1 | 10 | Requirements analysis; Process documentation; Stakeholder management
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Sales Product Matching | Update | Software Engineer | IT | Software Engineer 1 | 19 | Technical implementation; Code development; Unit testing
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Payment Execution | Delete | Business Analyst | IT | Business Analyst 1 | 7 | Requirements analysis; Process documentation; Stakeholder management
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Payment Execution | Delete | Software Engineer | IT | Software Engineer 1 | 7 | Technical implementation; Code development; Unit testing
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Payment Execution | Delete | Test Engineer | IT | Test Engineer 1 | 5 | Test planning; Test execution; Quality assurance
Innovation Program | Blockchain Cluster Migration v9 | IT | Cloud Native Storage (Rook/Longhorn) | Update | Business Analyst | IT | Business Analyst 1 | 10 | Requirements analysis; Process documentation; Stakeholder management
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Wealth Management | Update | Business Analyst | IT | Business Analyst 1 | 16 | Requirements analysis; Process documentation; Stakeholder management
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Wealth Management | Update | Software Engineer | IT | Software Engineer 1 | 23 | Technical implementation; Code development; Unit testing
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Wealth Management | Update | Test Engineer | IT | Test Engineer 1 | 17 | Test planning; Test execution; Quality assurance
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Loan Processing | Update | Business Analyst | IT | Business Analyst 1 | 12 | Requirements analysis; Process documentation; Stakeholder management
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Loan Processing | Update | Software Engineer | IT | Software Engineer 1 | 19 | Technical implementation; Code development; Unit testing
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Market Research | Create | Business Analyst | IT | Business Analyst 1 | 16 | Requirements analysis; Process documentation; Stakeholder management
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Market Research | Create | Software Engineer | IT | Software Engineer 1 | 24 | Technical implementation; Code development; Unit testing
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Customer Identity Management | Create | Business Analyst | IT | Business Analyst 1 | 22 | Requirements analysis; Process documentation; Stakeholder management
Innovation Program | Blockchain Cluster Migration v9 | IT | API Management | Create | Business Analyst | IT | Business Analyst 1 | 27 | Requirements analysis; Process documentation; Stakeholder management
Innovation Program | Blockchain Cluster Migration v9 | IT | API Management | Create | Software Engineer | IT | Software Engineer 1 | 25 | Technical implementation; Code development; Unit testing
Innovation Program | Blockchain Cluster Migration v9 | IT | API Management | Create | Test Engineer | IT | Test Engineer 1 | 26 | Test planning; Test execution; Quality assurance
Innovation Program | Blockchain Cluster Migration v9 | IT | Service Level Management | Update | Business Analyst | IT | Business Analyst 1 | 9 | Requirements analysis; Process documentation; Stakeholder management
Innovation Program | Blockchain Cluster Migration v9 | IT | Service Level Management | Update | Software Engineer | IT | Software Engineer 1 | 12 | Technical implementation; Code development; Unit testing
Innovation Program | Blockchain Cluster Migration v9 | IT | Service Level Management | Update | Test Engineer | IT | Test Engineer 1 | 10 | Test planning; Test execution; Quality assurance
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Channel Management | Update | Business Analyst | IT | Business Analyst 1 | 9 | Requirements analysis; Process documentation; Stakeholder management
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Channel Management | Update | Software Engineer | IT | Software Engineer 1 | 12 | Technical implementation; Code development; Unit testing
Innovation Program | Blockchain Cluster Migration v9 | BUSINESS | Channel Management | Update | Test Engineer | IT | Test Engineer 1 | 12 | Test planning; Test execution; Quality assurance