## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
Data Program | Data Lake Cluster Migration v11 | IT | Event Streaming (NATS/Kafka) | Create | Business Analyst | IT | Business Analyst 1 | 23 | Requirements analysis; Process documentation; Stakeholder management
Data Program | Data Lake Cluster Migration v11 | IT | Event Streaming (NATS/Kafka) | Create | Software Engineer | IT | Software Engineer 1 | 32 | Technical implementation; Code development; Unit testing
Data Program | Data Lake Cluster Migration v11 | BUSINESS | Customer Agreement | Update | Business Analyst | IT | Business Analyst 1 | 14 | Requirements analysis; Process documentation; Stakeholder management
Data Program | Data Lake Cluster Migration v11 | BUSINESS | Customer Agreement | Update | Software Engineer | IT | Software Engineer 1 | 15 | Technical implementation; Code development; Unit testing
Data Program | Data Lake Cluster Migration v11 | BUSINESS | Customer Agreement | Update | Test Engineer | IT | Test Engineer 1 | 13 | Test planning; Test execution; Quality assurance
Data Program | Data Lake Cluster Migration v11 | BUSINESS | Customer Agreement | Update | Solution Architect | IT | Solution Architect 1 | 9 | Architecture design; Technical guidance; Solution review
Data Program | Data Lake Cluster Migration v11 | BUSINESS | Customer Agreement | Update | Platform Engineer | IT | Platform Engineer 1 | 13 | Platform development; Infrastructure setup; Platform maintenance
Data Program | Data Lake Cluster Migration v11 | BUSINESS | Fraud Detection | Update | Business Analyst | IT | Business Analyst 1 | 10 | Requirements analysis; Process documentation; Stakeholder management
Data Program | Data Lake Cluster Migration v11 | BUSINESS | Fraud Detection | Update | Software Engineer | IT | Software Engineer 1 | 22 | Technical implementation; Code development; Unit testing
Data Program | Data Lake Cluster Migration v11 | BUSINESS | Fraud Detection | Update | Test Engineer | IT | Test Engineer 1 | 15 | Test planning; Test execution; Quality assurance
Data Program | Data Lake Cluster Migration v11 | BUSINESS | Fraud Detection | Update | Solution Architect | IT | Solution Architect 1 | 12 | Architecture design; Technical guidance; Solution review
Data Program | Data Lake Cluster Migration v11 | BUSINESS | Fraud Detection | Update | Platform Engineer | IT | Platform Engineer 1 | 19 | Platform development; Infrastructure setup; Platform maintenance
Data Program | Data Lake Cluster Migration v11 | IT | Monitoring & Event Management | Update | Business Analyst | IT | Business Analyst 1 | 9 | Requirements analysis; Process documentation; Stakeholder management
Data Program | Data Lake Cluster Migration v11 | IT | Monitoring & Event Management | Update | Software Engineer | IT | Software Engineer 1 | 22 | Technical implementation; Code development; Unit testing
Data Program | Data Lake Cluster Migration v11 | IT | Monitoring & Event Management | Update | Test Engineer | IT | Test Engineer 1 | 13 | Test planning; Test execution; Quality assurance
Data Program | Data Lake Cluster Migration v11 | IT | Monitoring & Event Management | Update | Solution Architect | IT | Solution Architect 1 | 17 | Architecture design; Technical guidance; Solution review
Data Program | Data Lake Cluster Migration v11 | IT | Container Orchestration (Kubernetes) | Delete | Business Analyst | IT | Business Analyst 1 | 6 | Requirements analysis; Process documentation; Stakeholder management
Data Program | Data Lake Cluster Migration v11 | IT | Container Orchestration (Kubernetes) | Delete | Software Engineer | IT | Software Engineer 1 | 7 | Technical implementation; Code development; Unit testing
Data Program | Data Lake Cluster Migration v11 | IT | Container Orchestration (Kubernetes) | Delete | Test Engineer | IT | Test Engineer 1 | 8 | Test planning; Test execution; Quality assurance
Data Program | Data Lake Cluster Migration v11 | BUSINESS | Regulatory Compliance | Delete | Business Analyst | IT | Business Analyst 1 | 7 | Requirements analysis; Process documentation; Stakeholder management
Data Program | Data Lake Cluster Migration v11 | BUSINESS | Account Management | Update | Business Analyst | IT | Business Analyst 1 | 11 | Requirements analysis; Process documentation; Stakeholder management
Data Program | Data Lake Cluster Migration v11 | BUSINESS | Account Management | Update | Software Engineer | IT | Software Engineer 1 | 12 | Technical implementation; Code development; Unit testing
Data Program | Data Lake Cluster Migration v11 | BUSINESS | Account Management | Update | Test Engineer | IT | Test Engineer 1 | 12 | Test planning; Test execution; Quality assurance
Data Program | Data Lake Cluster Migration v11 | BUSINESS | Account Management | Update | Solution Architect | IT | Solution Architect 1 | 10 | Architecture design; Technical guidance; Solution review
Data Program | Data Lake Cluster Migration v11 | BUSINESS | Account Management | Update | Platform Engineer | IT | Platform Engineer 1 | 13 | Platform development; Infrastructure setup; Platform maintenance
Data Program | Data Lake Cluster Migration v11 | IT | Serverless Platform (Knative/OpenFaaS) | Update | Business Analyst | IT | Business Analyst 1 | 9 | Requirements analysis; Process documentation; Stakeholder management
Data Program | Data Lake Cluster Migration v11 | IT | Serverless Platform (Knative/OpenFaaS) | Update | Software Engineer | IT | Software Engineer 1 | 16 | Technical implementation; Code development; Unit testing