## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
IT Core Program | Istio Cluster Migration v1 | IT | Service Mesh (Istio/Linkerd) | Create | Business Analyst | IT | Business Analyst 1 | 17 | Requirements analysis; Process documentation; Stakeholder management
IT Core Program | Istio Cluster Migration v1 | IT | Service Mesh (Istio/Linkerd) | Create | Software Engineer | IT | Software Engineer 1 | 27 | Technical implementation; Code development; Unit testing
IT Core Program | Istio Cluster Migration v1 | IT | Service Mesh (Istio/Linkerd) | Create | Test Engineer | IT | Test Engineer 1 | 20 | Test planning; Test execution; Quality assurance
IT Core Program | Istio Cluster Migration v1 | IT | Distributed Tracing (Jaeger/OpenTelemetry) | Update | Business Analyst | IT | Business Analyst 1 | 10 | Requirements analysis; Process documentation; Stakeholder management
IT Core Program | Istio Cluster Migration v1 | IT | Knowledge Management | Update | Business Analyst | IT | Business Analyst 1 | 9 | Requirements analysis; Process documentation; Stakeholder management
IT Core Program | Istio Cluster Migration v1 | BUSINESS | Market Research | Create | Business Analyst | IT | Business Analyst 1 | 23 | Requirements analysis; Process documentation; Stakeholder management
IT Core Program | Istio Cluster Migration v1 | BUSINESS | Market Research | Create | Software Engineer | IT | Software Engineer 1 | 35 | Technical implementation; Code development; Unit testing
IT Core Program | Istio Cluster Migration v1 | IT | IT Continuity Management | Create | Business Analyst | IT | Business Analyst 1 | 24 | Requirements analysis; Process documentation; Stakeholder management
IT Core Program | Istio Cluster Migration v1 | IT | IT Continuity Management | Create | Software Engineer | IT | Software Engineer 1 | 30 | Technical implementation; Code development; Unit testing
IT Core Program | Istio Cluster Migration v1 | IT | IT Continuity Management | Create | Test Engineer | IT | Test Engineer 1 | 17 | Test planning; Test execution; Quality assurance
IT Core Program | Istio Cluster Migration v1 | BUSINESS | Risk Management | Update | Business Analyst | IT | Business Analyst 1 | 10 | Requirements analysis; Process documentation; Stakeholder management
IT Core Program | Istio Cluster Migration v1 | BUSINESS | Payment Execution | Update | Business Analyst | IT | Business Analyst 1 | 9 | Requirements analysis; Process documentation; Stakeholder management
IT Core Program | Istio Cluster Migration v1 | BUSINESS | Payment Execution | Update | Software Engineer | IT | Software Engineer 1 | 12 | Technical implementation; Code development; Unit testing
IT Core Program | Istio Cluster Migration v1 | BUSINESS | Payment Execution | Update | Test Engineer | IT | Test Engineer 1 | 13 | Test planning; Test execution; Quality assurance
IT Core Program | Istio Cluster Migration v1 | IT | API Gateway (Envoy/Contour) | Create | Business Analyst | IT | Business Analyst 1 | 24 | Requirements analysis; Process documentation; Stakeholder management
IT Core Program | Istio Cluster Migration v1 | IT | IT Asset Management | Update | Business Analyst | IT | Business Analyst 1 | 10 | Requirements analysis; Process documentation; Stakeholder management
IT Core Program | Istio Cluster Migration v1 | IT | DevOps Management | Update | Business Analyst | IT | Business Analyst 1 | 11 | Requirements analysis; Process documentation; Stakeholder management
IT Core Program | Istio Cluster Migration v1 | IT | DevOps Management | Update | Software Engineer | IT | Software Engineer 1 | 13 | Technical implementation; Code development; Unit testing