## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Business Analyst | IT | Business Analyst 1 | 24 | Requirements analysis; Process documentation; Stakeholder management
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Product Owner | IT | Product Owner 1 | 19 | Backlog management; Feature prioritization; Value assessment
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Product Owner | IT | Product Owner 2 | 18 | Backlog management; Feature prioritization; Value assessment
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Business Process Expert | IT | Business Process Expert 1 | 24 | Process optimization; Business rules definition; Process implementation
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Compliance Officer | IT | Compliance Officer 1 | 18 | Compliance review; Regulatory assessment; Control documentation
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Risk Analyst | IT | Risk Analyst 1 | 12 | Risk assessment; Control design; Risk monitoring
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Risk Analyst | IT | Risk Analyst 2 | 11 | Risk assessment; Control design; Risk monitoring
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Software Engineer | IT | Software Engineer 1 | 26 | Technical implementation; Code development; Unit testing
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Test Engineer | IT | Test Engineer 1 | 27 | Test planning; Test execution; Quality assurance
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Test Engineer | IT | Test Engineer 2 | 19 | Test planning; Test execution; Quality assurance
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Test Engineer | IT | Test Engineer 3 | 30 | Test planning; Test execution; Quality assurance
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Test Engineer | IT | Test Engineer 4 | 22 | Test planning; Test execution; Quality assurance
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Solution Architect | IT | Solution Architect 1 | 30 | Architecture design; Technical guidance; Solution review
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Solution Architect | IT | Solution Architect 2 | 25 | Architecture design; Technical guidance; Solution review
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Platform Engineer | IT | Platform Engineer 1 | 20 | Platform development; Infrastructure setup; Platform maintenance
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Platform Engineer | IT | Platform Engineer 2 | 26 | Platform development; Infrastructure setup; Platform maintenance
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Platform Engineer | IT | Platform Engineer 3 | 21 | Platform development; Infrastructure setup; Platform maintenance
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Site Reliability Engineer | IT | Site Reliability Engineer 1 | 29 | Reliability monitoring; Performance optimization; Incident response
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Site Reliability Engineer | IT | Site Reliability Engineer 2 | 26 | Reliability monitoring; Performance optimization; Incident response
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Product Pricing | Create | Security Engineer | IT | Security Engineer 1 | 24 | Security implementation; Security testing; Security monitoring
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Risk Management | Delete | Business Analyst | IT | Business Analyst 1 | 6 | Requirements analysis; Process documentation; Stakeholder management
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Risk Management | Delete | Product Owner | IT | Product Owner 1 | 4 | Backlog management; Feature prioritization; Value assessment
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Risk Management | Delete | Business Process Expert | IT | Business Process Expert 1 | 3 | Process optimization; Business rules definition; Process implementation
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Risk Management | Delete | Compliance Officer | IT | Compliance Officer 1 | 4 | Compliance review; Regulatory assessment; Control documentation
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Risk Management | Delete | Software Engineer | IT | Software Engineer 1 | 6 | Technical implementation; Code development; Unit testing
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Risk Management | Delete | Test Engineer | IT | Test Engineer 1 | 8 | Test planning; Test execution; Quality assurance
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Risk Management | Delete | Solution Architect | IT | Solution Architect 1 | 6 | Architecture design; Technical guidance; Solution review
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Risk Management | Delete | Platform Engineer | IT | Platform Engineer 1 | 8 | Platform development; Infrastructure setup; Platform maintenance
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Risk Management | Delete | Site Reliability Engineer | IT | Site Reliability Engineer 1 | 6 | Reliability monitoring; Performance optimization; Incident response
IT Core Program | Kubernetes Cluster Migration v8 | BUSINESS | Risk Management | Delete | Security Engineer | IT | Security Engineer 1 | 8 | Security implementation; Security testing; Security monitoring