## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
KYC-KYT Program | KYC-KYT Cluster Upgrade v1 | BUSINESS | Risk Management | Create | Business Analyst | IT | Business Analyst 1 | 19 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v1 | BUSINESS | Channel Management | Update | Business Analyst | IT | Business Analyst 1 | 15 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v1 | BUSINESS | Channel Management | Update | Product Owner | IT | Product Owner 1 | 9 | Backlog management; Feature prioritization; Value assessment
KYC-KYT Program | KYC-KYT Cluster Upgrade v1 | BUSINESS | Channel Management | Update | Business Process Expert | IT | Business Process Expert 1 | 15 | Process optimization; Business rules definition; Process implementation
KYC-KYT Program | KYC-KYT Cluster Upgrade v1 | BUSINESS | Channel Management | Update | Compliance Officer | IT | Compliance Officer 1 | 10 | Compliance review; Regulatory assessment; Control documentation
KYC-KYT Program | KYC-KYT Cluster Upgrade v1 | BUSINESS | Channel Management | Update | Software Engineer | IT | Software Engineer 1 | 15 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v1 | BUSINESS | Channel Management | Update | Test Engineer | IT | Test Engineer 1 | 18 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v1 | BUSINESS | Channel Management | Update | Solution Architect | IT | Solution Architect 1 | 9 | Architecture design; Technical guidance; Solution review
KYC-KYT Program | KYC-KYT Cluster Upgrade v1 | BUSINESS | Channel Management | Update | Platform Engineer | IT | Platform Engineer 1 | 14 | Platform development; Infrastructure setup; Platform maintenance
KYC-KYT Program | KYC-KYT Cluster Upgrade v1 | BUSINESS | Channel Management | Update | Site Reliability Engineer | IT | Site Reliability Engineer 1 | 13 | Reliability monitoring; Performance optimization; Incident response
KYC-KYT Program | KYC-KYT Cluster Upgrade v1 | IT | Service Desk | Update | Business Analyst | IT | Business Analyst 1 | 15 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v1 | BUSINESS | Customer Onboarding | Create | Business Analyst | IT | Business Analyst 1 | 25 | Requirements analysis; Process documentation; Stakeholder management