## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Collateral Management | Delete | Business Analyst | IT | Business Analyst 1 | 8 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Customer Agreement | Create | Business Analyst | IT | Business Analyst 1 | 24 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Customer Agreement | Create | Software Engineer | IT | Software Engineer 1 | 39 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Customer Agreement | Create | Test Engineer | IT | Test Engineer 1 | 15 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Investment Portfolio Management | Delete | Business Analyst | IT | Business Analyst 1 | 8 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Investment Portfolio Management | Delete | Product Owner | IT | Product Owner 1 | 4 | Backlog management; Feature prioritization; Value assessment
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Investment Portfolio Management | Delete | Software Engineer | IT | Software Engineer 1 | 8 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Investment Portfolio Management | Delete | Test Engineer | IT | Test Engineer 1 | 6 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Investment Portfolio Management | Delete | Solution Architect | IT | Solution Architect 1 | 6 | Architecture design; Technical guidance; Solution review
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Investment Portfolio Management | Delete | Platform Engineer | IT | Platform Engineer 1 | 8 | Platform development; Infrastructure setup; Platform maintenance
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Wealth Management | Create | Business Analyst | IT | Business Analyst 1 | 28 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Wealth Management | Create | Software Engineer | IT | Software Engineer 1 | 39 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Wealth Management | Create | Test Engineer | IT | Test Engineer 1 | 25 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Document Management | Update | Business Analyst | IT | Business Analyst 1 | 17 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Document Management | Update | Product Owner | IT | Product Owner 1 | 6 | Backlog management; Feature prioritization; Value assessment
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Document Management | Update | Software Engineer | IT | Software Engineer 1 | 16 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Document Management | Update | Test Engineer | IT | Test Engineer 1 | 13 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Document Management | Update | Solution Architect | IT | Solution Architect 1 | 13 | Architecture design; Technical guidance; Solution review
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Document Management | Update | Platform Engineer | IT | Platform Engineer 1 | 12 | Platform development; Infrastructure setup; Platform maintenance
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Financial Accounting | Update | Business Analyst | IT | Business Analyst 1 | 16 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v12 | BUSINESS | Financial Accounting | Update | Software Engineer | IT | Software Engineer 1 | 15 | Technical implementation; Code development; Unit testing