## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | Serverless Platform (Knative/OpenFaaS) | Delete | Business Analyst | IT | Business Analyst 1 | 7 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | Cloud Native Storage (Rook/Longhorn) | Delete | Business Analyst | IT | Business Analyst 1 | 5 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | Cloud Native Storage (Rook/Longhorn) | Delete | Software Engineer | IT | Software Engineer 1 | 7 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | Cloud Native Storage (Rook/Longhorn) | Delete | Test Engineer | IT | Test Engineer 1 | 9 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | BUSINESS | Financial Accounting | Create | Business Analyst | IT | Business Analyst 1 | 23 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | BUSINESS | Card Authorization | Update | Business Analyst | IT | Business Analyst 1 | 11 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | Auto-scaling (KEDA/Cluster Autoscaler) | Delete | Business Analyst | IT | Business Analyst 1 | 5 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | Event Streaming (NATS/Kafka) | Delete | Business Analyst | IT | Business Analyst 1 | 7 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | Event Streaming (NATS/Kafka) | Delete | Software Engineer | IT | Software Engineer 1 | 8 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | API Management | Update | Business Analyst | IT | Business Analyst 1 | 9 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | Incident Management | Create | Business Analyst | IT | Business Analyst 1 | 19 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | Incident Management | Create | Software Engineer | IT | Software Engineer 1 | 31 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | IT Asset Management | Delete | Business Analyst | IT | Business Analyst 1 | 4 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | IT Asset Management | Delete | Software Engineer | IT | Software Engineer 1 | 7 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | IT Asset Management | Delete | Test Engineer | IT | Test Engineer 1 | 6 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | Release Management | Update | Business Analyst | IT | Business Analyst 1 | 12 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | Security Policy Enforcement (OPA/Falco) | Update | Business Analyst | IT | Business Analyst 1 | 13 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | Security Policy Enforcement (OPA/Falco) | Update | Software Engineer | IT | Software Engineer 1 | 12 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | Security Policy Enforcement (OPA/Falco) | Update | Test Engineer | IT | Test Engineer 1 | 15 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | Problem Management | Delete | Business Analyst | IT | Business Analyst 1 | 6 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | Problem Management | Delete | Software Engineer | IT | Software Engineer 1 | 10 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v14 | IT | Service Validation & Testing | Update | Business Analyst | IT | Business Analyst 1 | 12 | Requirements analysis; Process documentation; Stakeholder management