## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | IT | IT Asset Management | Update | Business Analyst | IT | Business Analyst 1 | 12 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | IT | IT Asset Management | Update | Software Engineer | IT | Software Engineer 1 | 14 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | IT | IT Asset Management | Update | Test Engineer | IT | Test Engineer 1 | 13 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | IT | IT Asset Management | Update | Solution Architect | IT | Solution Architect 1 | 9 | Architecture design; Technical guidance; Solution review
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | IT | IT Asset Management | Update | Platform Engineer | IT | Platform Engineer 1 | 16 | Platform development; Infrastructure setup; Platform maintenance
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Customer Agreement | Update | Business Analyst | IT | Business Analyst 1 | 14 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Customer Agreement | Update | Software Engineer | IT | Software Engineer 1 | 21 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Customer Agreement | Update | Test Engineer | IT | Test Engineer 1 | 12 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Investment Portfolio Management | Create | Business Analyst | IT | Business Analyst 1 | 25 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Investment Portfolio Management | Create | Product Owner | IT | Product Owner 1 | 14 | Backlog management; Feature prioritization; Value assessment
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Investment Portfolio Management | Create | Software Engineer | IT | Software Engineer 1 | 35 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Investment Portfolio Management | Create | Test Engineer | IT | Test Engineer 1 | 27 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Investment Portfolio Management | Create | Solution Architect | IT | Solution Architect 1 | 17 | Architecture design; Technical guidance; Solution review
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Investment Portfolio Management | Create | Platform Engineer | IT | Platform Engineer 1 | 20 | Platform development; Infrastructure setup; Platform maintenance
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Financial Accounting | Delete | Business Analyst | IT | Business Analyst 1 | 7 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Financial Accounting | Delete | Software Engineer | IT | Software Engineer 1 | 6 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Financial Accounting | Delete | Test Engineer | IT | Test Engineer 1 | 6 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Financial Accounting | Delete | Solution Architect | IT | Solution Architect 1 | 4 | Architecture design; Technical guidance; Solution review
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Financial Accounting | Delete | Platform Engineer | IT | Platform Engineer 1 | 7 | Platform development; Infrastructure setup; Platform maintenance
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Loan Processing | Update | Business Analyst | IT | Business Analyst 1 | 13 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Loan Processing | Update | Product Owner | IT | Product Owner 1 | 6 | Backlog management; Feature prioritization; Value assessment
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Loan Processing | Update | Software Engineer | IT | Software Engineer 1 | 15 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Loan Processing | Update | Test Engineer | IT | Test Engineer 1 | 16 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Loan Processing | Update | Solution Architect | IT | Solution Architect 1 | 10 | Architecture design; Technical guidance; Solution review
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Loan Processing | Update | Platform Engineer | IT | Platform Engineer 1 | 12 | Platform development; Infrastructure setup; Platform maintenance
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Loan Processing | Update | Site Reliability Engineer | IT | Site Reliability Engineer 1 | 9 | Reliability monitoring; Performance optimization; Incident response
KYC-KYT Program | KYC-KYT Cluster Upgrade v2 | BUSINESS | Loan Processing | Update | Security Engineer | IT | Security Engineer 1 | 12 | Security implementation; Security testing; Security monitoring