## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Trade Settlement | Delete | Business Analyst | IT | Business Analyst 1 | 5 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Trade Settlement | Delete | Product Owner | IT | Product Owner 1 | 4 | Backlog management; Feature prioritization; Value assessment
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Trade Settlement | Delete | Software Engineer | IT | Software Engineer 1 | 8 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Trade Settlement | Delete | Test Engineer | IT | Test Engineer 1 | 8 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Trade Settlement | Delete | Solution Architect | IT | Solution Architect 1 | 6 | Architecture design; Technical guidance; Solution review
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Trade Settlement | Delete | Platform Engineer | IT | Platform Engineer 1 | 9 | Platform development; Infrastructure setup; Platform maintenance
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Regulatory Compliance | Create | Business Analyst | IT | Business Analyst 1 | 19 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Regulatory Compliance | Create | Product Owner | IT | Product Owner 1 | 10 | Backlog management; Feature prioritization; Value assessment
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Regulatory Compliance | Create | Business Process Expert | IT | Business Process Expert 1 | 14 | Process optimization; Business rules definition; Process implementation
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Regulatory Compliance | Create | Software Engineer | IT | Software Engineer 1 | 33 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Regulatory Compliance | Create | Test Engineer | IT | Test Engineer 1 | 23 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Regulatory Compliance | Create | Solution Architect | IT | Solution Architect 1 | 21 | Architecture design; Technical guidance; Solution review
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Regulatory Compliance | Create | Platform Engineer | IT | Platform Engineer 1 | 34 | Platform development; Infrastructure setup; Platform maintenance
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Regulatory Compliance | Create | Site Reliability Engineer | IT | Site Reliability Engineer 1 | 19 | Reliability monitoring; Performance optimization; Incident response
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Account Management | Create | Business Analyst | IT | Business Analyst 1 | 26 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Account Management | Create | Product Owner | IT | Product Owner 1 | 17 | Backlog management; Feature prioritization; Value assessment
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Account Management | Create | Business Process Expert | IT | Business Process Expert 1 | 12 | Process optimization; Business rules definition; Process implementation
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Account Management | Create | Software Engineer | IT | Software Engineer 1 | 22 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Account Management | Create | Test Engineer | IT | Test Engineer 1 | 23 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Account Management | Create | Test Engineer | IT | Test Engineer 2 | 18 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Account Management | Create | Solution Architect | IT | Solution Architect 1 | 30 | Architecture design; Technical guidance; Solution review
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Account Management | Create | Platform Engineer | IT | Platform Engineer 1 | 26 | Platform development; Infrastructure setup; Platform maintenance
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Account Management | Create | Site Reliability Engineer | IT | Site Reliability Engineer 1 | 22 | Reliability monitoring; Performance optimization; Incident response
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Account Management | Create | Security Engineer | IT | Security Engineer 1 | 24 | Security implementation; Security testing; Security monitoring
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Financial Accounting | Create | Business Analyst | IT | Business Analyst 1 | 23 | Requirements analysis; Process documentation; Stakeholder management
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Financial Accounting | Create | Product Owner | IT | Product Owner 1 | 10 | Backlog management; Feature prioritization; Value assessment
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Financial Accounting | Create | Business Process Expert | IT | Business Process Expert 1 | 25 | Process optimization; Business rules definition; Process implementation
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Financial Accounting | Create | Software Engineer | IT | Software Engineer 1 | 39 | Technical implementation; Code development; Unit testing
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Financial Accounting | Create | Test Engineer | IT | Test Engineer 1 | 21 | Test planning; Test execution; Quality assurance
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Financial Accounting | Create | Solution Architect | IT | Solution Architect 1 | 20 | Architecture design; Technical guidance; Solution review
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Financial Accounting | Create | Platform Engineer | IT | Platform Engineer 1 | 23 | Platform development; Infrastructure setup; Platform maintenance
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Financial Accounting | Create | Platform Engineer | IT | Platform Engineer 2 | 27 | Platform development; Infrastructure setup; Platform maintenance
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Financial Accounting | Create | Site Reliability Engineer | IT | Site Reliability Engineer 1 | 17 | Reliability monitoring; Performance optimization; Incident response
KYC-KYT Program | KYC-KYT Cluster Upgrade v8 | BUSINESS | Financial Accounting | Create | Security Engineer | IT | Security Engineer 1 | 20 | Security implementation; Security testing; Security monitoring