## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Business Analyst | IT | Business Analyst 1 | 15 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Product Owner | IT | Product Owner 1 | 10 | Backlog management; Feature prioritization; Value assessment
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Product Owner | IT | Product Owner 2 | 12 | Backlog management; Feature prioritization; Value assessment
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Business Process Expert | IT | Business Process Expert 1 | 7 | Process optimization; Business rules definition; Process implementation
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Business Process Expert | IT | Business Process Expert 2 | 8 | Process optimization; Business rules definition; Process implementation
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Business Process Expert | IT | Business Process Expert 3 | 9 | Process optimization; Business rules definition; Process implementation
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Compliance Officer | IT | Compliance Officer 1 | 6 | Compliance review; Regulatory assessment; Control documentation
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Compliance Officer | IT | Compliance Officer 2 | 7 | Compliance review; Regulatory assessment; Control documentation
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Risk Analyst | IT | Risk Analyst 1 | 6 | Risk assessment; Control design; Risk monitoring
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Risk Analyst | IT | Risk Analyst 2 | 6 | Risk assessment; Control design; Risk monitoring
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Risk Analyst | IT | Risk Analyst 3 | 12 | Risk assessment; Control design; Risk monitoring
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Risk Analyst | IT | Risk Analyst 4 | 9 | Risk assessment; Control design; Risk monitoring
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Software Engineer | IT | Software Engineer 1 | 13 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Software Engineer | IT | Software Engineer 2 | 16 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Software Engineer | IT | Software Engineer 3 | 18 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Test Engineer | IT | Test Engineer 1 | 16 | Test planning; Test execution; Quality assurance
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Test Engineer | IT | Test Engineer 2 | 11 | Test planning; Test execution; Quality assurance
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Solution Architect | IT | Solution Architect 1 | 12 | Architecture design; Technical guidance; Solution review
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Solution Architect | IT | Solution Architect 2 | 12 | Architecture design; Technical guidance; Solution review
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Solution Architect | IT | Solution Architect 3 | 16 | Architecture design; Technical guidance; Solution review
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Solution Architect | IT | Solution Architect 4 | 14 | Architecture design; Technical guidance; Solution review
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Platform Engineer | IT | Platform Engineer 1 | 20 | Platform development; Infrastructure setup; Platform maintenance
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Site Reliability Engineer | IT | Site Reliability Engineer 1 | 9 | Reliability monitoring; Performance optimization; Incident response
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Site Reliability Engineer | IT | Site Reliability Engineer 2 | 16 | Reliability monitoring; Performance optimization; Incident response
Market Mandatory Program | Market Cluster Migration v12 | IT | Service Desk | Update | Security Engineer | IT | Security Engineer 1 | 17 | Security implementation; Security testing; Security monitoring