## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
Market Mandatory Program | Market Cluster Migration v17 | BUSINESS | Product Pricing | Delete | Business Analyst | IT | Business Analyst 1 | 6 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v17 | BUSINESS | Product Pricing | Delete | Software Engineer | IT | Software Engineer 1 | 6 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v17 | BUSINESS | Account Management | Delete | Business Analyst | IT | Business Analyst 1 | 6 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v17 | BUSINESS | Regulatory Compliance | Create | Business Analyst | IT | Business Analyst 1 | 18 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v17 | BUSINESS | Regulatory Compliance | Create | Software Engineer | IT | Software Engineer 1 | 34 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v17 | IT | Cloud Native Storage (Rook/Longhorn) | Update | Business Analyst | IT | Business Analyst 1 | 15 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v17 | IT | Cloud Native Storage (Rook/Longhorn) | Update | Software Engineer | IT | Software Engineer 1 | 16 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v17 | IT | Security Policy Enforcement (OPA/Falco) | Delete | Business Analyst | IT | Business Analyst 1 | 7 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v17 | IT | Security Policy Enforcement (OPA/Falco) | Delete | Software Engineer | IT | Software Engineer 1 | 9 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v17 | BUSINESS | Customer Identity Management | Update | Business Analyst | IT | Business Analyst 1 | 14 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v17 | BUSINESS | Customer Identity Management | Update | Software Engineer | IT | Software Engineer 1 | 13 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v17 | IT | Cloud Native CI/CD (Tekton/Spinnaker) | Update | Business Analyst | IT | Business Analyst 1 | 13 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v17 | IT | Cloud Native CI/CD (Tekton/Spinnaker) | Update | Software Engineer | IT | Software Engineer 1 | 13 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v17 | IT | Security Management | Create | Business Analyst | IT | Business Analyst 1 | 20 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v17 | IT | Security Management | Create | Software Engineer | IT | Software Engineer 1 | 25 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v17 | BUSINESS | Risk Management | Update | Business Analyst | IT | Business Analyst 1 | 9 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v17 | BUSINESS | Risk Management | Update | Software Engineer | IT | Software Engineer 1 | 16 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v17 | BUSINESS | Financial Accounting | Update | Business Analyst | IT | Business Analyst 1 | 12 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v17 | BUSINESS | Loan Processing | Update | Business Analyst | IT | Business Analyst 1 | 12 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v17 | BUSINESS | Fraud Detection | Delete | Business Analyst | IT | Business Analyst 1 | 7 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v17 | BUSINESS | Fraud Detection | Delete | Software Engineer | IT | Software Engineer 1 | 9 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v17 | BUSINESS | Wealth Management | Create | Business Analyst | IT | Business Analyst 1 | 30 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v17 | BUSINESS | Wealth Management | Create | Software Engineer | IT | Software Engineer 1 | 24 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v17 | BUSINESS | Document Management | Delete | Business Analyst | IT | Business Analyst 1 | 9 | Requirements analysis; Process documentation; Stakeholder management