## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
Market Mandatory Program | Market Cluster Migration v8 | IT | Problem Management | Create | Business Analyst | IT | Business Analyst 1 | 22 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v8 | BUSINESS | Investment Portfolio Management | Delete | Business Analyst | IT | Business Analyst 1 | 9 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v8 | BUSINESS | Investment Portfolio Management | Delete | Software Engineer | IT | Software Engineer 1 | 7 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v8 | BUSINESS | Investment Portfolio Management | Delete | Test Engineer | IT | Test Engineer 1 | 7 | Test planning; Test execution; Quality assurance
Market Mandatory Program | Market Cluster Migration v8 | IT | Release Management | Delete | Business Analyst | IT | Business Analyst 1 | 6 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v8 | IT | Release Management | Delete | Software Engineer | IT | Software Engineer 1 | 10 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v8 | IT | Release Management | Delete | Test Engineer | IT | Test Engineer 1 | 4 | Test planning; Test execution; Quality assurance
Market Mandatory Program | Market Cluster Migration v8 | BUSINESS | Channel Management | Create | Business Analyst | IT | Business Analyst 1 | 28 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v8 | BUSINESS | Channel Management | Create | Software Engineer | IT | Software Engineer 1 | 40 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v8 | IT | Service Desk | Create | Business Analyst | IT | Business Analyst 1 | 20 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v8 | IT | Service Desk | Create | Product Owner | IT | Product Owner 1 | 18 | Backlog management; Feature prioritization; Value assessment
Market Mandatory Program | Market Cluster Migration v8 | IT | Service Desk | Create | Software Engineer | IT | Software Engineer 1 | 30 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v8 | IT | Service Desk | Create | Test Engineer | IT | Test Engineer 1 | 23 | Test planning; Test execution; Quality assurance
Market Mandatory Program | Market Cluster Migration v8 | IT | Service Desk | Create | Solution Architect | IT | Solution Architect 1 | 15 | Architecture design; Technical guidance; Solution review
Market Mandatory Program | Market Cluster Migration v8 | BUSINESS | Market Research | Update | Business Analyst | IT | Business Analyst 1 | 9 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v8 | BUSINESS | Market Research | Update | Software Engineer | IT | Software Engineer 1 | 16 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v8 | BUSINESS | Market Research | Update | Test Engineer | IT | Test Engineer 1 | 14 | Test planning; Test execution; Quality assurance
Market Mandatory Program | Market Cluster Migration v8 | BUSINESS | Market Research | Update | Solution Architect | IT | Solution Architect 1 | 13 | Architecture design; Technical guidance; Solution review
Market Mandatory Program | Market Cluster Migration v8 | BUSINESS | Fraud Detection | Update | Business Analyst | IT | Business Analyst 1 | 14 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v8 | BUSINESS | Fraud Detection | Update | Software Engineer | IT | Software Engineer 1 | 19 | Technical implementation; Code development; Unit testing
Market Mandatory Program | Market Cluster Migration v8 | BUSINESS | Regulatory Compliance | Create | Business Analyst | IT | Business Analyst 1 | 21 | Requirements analysis; Process documentation; Stakeholder management
Market Mandatory Program | Market Cluster Migration v8 | BUSINESS | Regulatory Compliance | Create | Software Engineer | IT | Software Engineer 1 | 25 | Technical implementation; Code development; Unit testing