## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
Digital Program | Mobile Cluster Migration v5 | IT | Service Desk | Create | Business Analyst | IT | Business Analyst 1 | 19 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | Mobile Cluster Migration v5 | IT | Continuous Delivery (Argo/Flux) | Update | Business Analyst | IT | Business Analyst 1 | 12 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | Mobile Cluster Migration v5 | IT | Workload Scheduling (KubeEdge/Volcano) | Create | Business Analyst | IT | Business Analyst 1 | 29 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | Mobile Cluster Migration v5 | IT | Workload Scheduling (KubeEdge/Volcano) | Create | Software Engineer | IT | Software Engineer 1 | 36 | Technical implementation; Code development; Unit testing
Digital Program | Mobile Cluster Migration v5 | IT | Workload Scheduling (KubeEdge/Volcano) | Create | Test Engineer | IT | Test Engineer 1 | 30 | Test planning; Test execution; Quality assurance
Digital Program | Mobile Cluster Migration v5 | IT | IT Continuity Management | Update | Business Analyst | IT | Business Analyst 1 | 13 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | Mobile Cluster Migration v5 | IT | IT Continuity Management | Update | Software Engineer | IT | Software Engineer 1 | 14 | Technical implementation; Code development; Unit testing
Digital Program | Mobile Cluster Migration v5 | BUSINESS | Account Management | Create | Business Analyst | IT | Business Analyst 1 | 17 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | Mobile Cluster Migration v5 | BUSINESS | Account Management | Create | Software Engineer | IT | Software Engineer 1 | 36 | Technical implementation; Code development; Unit testing
Digital Program | Mobile Cluster Migration v5 | BUSINESS | Account Management | Create | Test Engineer | IT | Test Engineer 1 | 28 | Test planning; Test execution; Quality assurance
Digital Program | Mobile Cluster Migration v5 | IT | Event Streaming (NATS/Kafka) | Update | Business Analyst | IT | Business Analyst 1 | 10 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | Mobile Cluster Migration v5 | IT | Event Streaming (NATS/Kafka) | Update | Software Engineer | IT | Software Engineer 1 | 16 | Technical implementation; Code development; Unit testing
Digital Program | Mobile Cluster Migration v5 | IT | Service Configuration Management | Delete | Business Analyst | IT | Business Analyst 1 | 6 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | Mobile Cluster Migration v5 | IT | Service Configuration Management | Delete | Software Engineer | IT | Software Engineer 1 | 11 | Technical implementation; Code development; Unit testing
Digital Program | Mobile Cluster Migration v5 | IT | Security Policy Enforcement (OPA/Falco) | Update | Business Analyst | IT | Business Analyst 1 | 9 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | Mobile Cluster Migration v5 | IT | Security Policy Enforcement (OPA/Falco) | Update | Software Engineer | IT | Software Engineer 1 | 21 | Technical implementation; Code development; Unit testing
Digital Program | Mobile Cluster Migration v5 | IT | Security Policy Enforcement (OPA/Falco) | Update | Test Engineer | IT | Test Engineer 1 | 15 | Test planning; Test execution; Quality assurance
Digital Program | Mobile Cluster Migration v5 | BUSINESS | Payment Execution | Create | Business Analyst | IT | Business Analyst 1 | 19 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | Mobile Cluster Migration v5 | BUSINESS | Payment Execution | Create | Software Engineer | IT | Software Engineer 1 | 26 | Technical implementation; Code development; Unit testing
Digital Program | Mobile Cluster Migration v5 | BUSINESS | Payment Execution | Create | Test Engineer | IT | Test Engineer 1 | 19 | Test planning; Test execution; Quality assurance
Digital Program | Mobile Cluster Migration v5 | IT | Secret Management (Vault/Secrets Store CSI) | Create | Business Analyst | IT | Business Analyst 1 | 26 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | Mobile Cluster Migration v5 | IT | Package Management (Helm/Brigade) | Create | Business Analyst | IT | Business Analyst 1 | 29 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | Mobile Cluster Migration v5 | IT | Service Level Management | Create | Business Analyst | IT | Business Analyst 1 | 21 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | Mobile Cluster Migration v5 | IT | IT Asset Management | Delete | Business Analyst | IT | Business Analyst 1 | 5 | Requirements analysis; Process documentation; Stakeholder management
Digital Program | Mobile Cluster Migration v5 | IT | IT Asset Management | Delete | Software Engineer | IT | Software Engineer 1 | 10 | Technical implementation; Code development; Unit testing