## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
Regulatory Program | Regulatory Cluster Migration v13 | IT | Cloud Native Storage (Rook/Longhorn) | Delete | Business Analyst | IT | Business Analyst 1 | 6 | Requirements analysis; Process documentation; Stakeholder management
Regulatory Program | Regulatory Cluster Migration v13 | IT | Cloud Native Storage (Rook/Longhorn) | Delete | Software Engineer | IT | Software Engineer 1 | 10 | Technical implementation; Code development; Unit testing
Regulatory Program | Regulatory Cluster Migration v13 | IT | Cloud Native Storage (Rook/Longhorn) | Delete | Test Engineer | IT | Test Engineer 1 | 7 | Test planning; Test execution; Quality assurance
Regulatory Program | Regulatory Cluster Migration v13 | IT | Cloud Native Storage (Rook/Longhorn) | Delete | Solution Architect | IT | Solution Architect 1 | 6 | Architecture design; Technical guidance; Solution review
Regulatory Program | Regulatory Cluster Migration v13 | IT | Release Management | Delete | Business Analyst | IT | Business Analyst 1 | 9 | Requirements analysis; Process documentation; Stakeholder management
Regulatory Program | Regulatory Cluster Migration v13 | IT | Release Management | Delete | Software Engineer | IT | Software Engineer 1 | 6 | Technical implementation; Code development; Unit testing
Regulatory Program | Regulatory Cluster Migration v13 | IT | Service Desk | Create | Business Analyst | IT | Business Analyst 1 | 20 | Requirements analysis; Process documentation; Stakeholder management
Regulatory Program | Regulatory Cluster Migration v13 | IT | Service Desk | Create | Product Owner | IT | Product Owner 1 | 18 | Backlog management; Feature prioritization; Value assessment
Regulatory Program | Regulatory Cluster Migration v13 | IT | Service Desk | Create | Software Engineer | IT | Software Engineer 1 | 24 | Technical implementation; Code development; Unit testing
Regulatory Program | Regulatory Cluster Migration v13 | IT | Service Desk | Create | Test Engineer | IT | Test Engineer 1 | 19 | Test planning; Test execution; Quality assurance
Regulatory Program | Regulatory Cluster Migration v13 | IT | Service Desk | Create | Solution Architect | IT | Solution Architect 1 | 21 | Architecture design; Technical guidance; Solution review
Regulatory Program | Regulatory Cluster Migration v13 | IT | Container Registry (Harbor/Dragonfly) | Delete | Business Analyst | IT | Business Analyst 1 | 8 | Requirements analysis; Process documentation; Stakeholder management
Regulatory Program | Regulatory Cluster Migration v13 | IT | Container Registry (Harbor/Dragonfly) | Delete | Product Owner | IT | Product Owner 1 | 3 | Backlog management; Feature prioritization; Value assessment
Regulatory Program | Regulatory Cluster Migration v13 | IT | Container Registry (Harbor/Dragonfly) | Delete | Software Engineer | IT | Software Engineer 1 | 7 | Technical implementation; Code development; Unit testing
Regulatory Program | Regulatory Cluster Migration v13 | IT | Container Registry (Harbor/Dragonfly) | Delete | Test Engineer | IT | Test Engineer 1 | 6 | Test planning; Test execution; Quality assurance
Regulatory Program | Regulatory Cluster Migration v13 | IT | Container Registry (Harbor/Dragonfly) | Delete | Solution Architect | IT | Solution Architect 1 | 8 | Architecture design; Technical guidance; Solution review
Regulatory Program | Regulatory Cluster Migration v13 | IT | Event Streaming (NATS/Kafka) | Create | Business Analyst | IT | Business Analyst 1 | 23 | Requirements analysis; Process documentation; Stakeholder management
Regulatory Program | Regulatory Cluster Migration v13 | IT | Cloud Management | Update | Business Analyst | IT | Business Analyst 1 | 12 | Requirements analysis; Process documentation; Stakeholder management
Regulatory Program | Regulatory Cluster Migration v13 | IT | Cloud Management | Update | Software Engineer | IT | Software Engineer 1 | 15 | Technical implementation; Code development; Unit testing
Regulatory Program | Regulatory Cluster Migration v13 | IT | Cloud Management | Update | Test Engineer | IT | Test Engineer 1 | 14 | Test planning; Test execution; Quality assurance
Regulatory Program | Regulatory Cluster Migration v13 | IT | Cloud Management | Update | Solution Architect | IT | Solution Architect 1 | 17 | Architecture design; Technical guidance; Solution review
Regulatory Program | Regulatory Cluster Migration v13 | IT | Cloud Management | Update | Platform Engineer | IT | Platform Engineer 1 | 19 | Platform development; Infrastructure setup; Platform maintenance
Regulatory Program | Regulatory Cluster Migration v13 | IT | Application Management | Create | Business Analyst | IT | Business Analyst 1 | 30 | Requirements analysis; Process documentation; Stakeholder management
Regulatory Program | Regulatory Cluster Migration v13 | IT | Application Management | Create | Product Owner | IT | Product Owner 1 | 19 | Backlog management; Feature prioritization; Value assessment
Regulatory Program | Regulatory Cluster Migration v13 | IT | Application Management | Create | Software Engineer | IT | Software Engineer 1 | 22 | Technical implementation; Code development; Unit testing
Regulatory Program | Regulatory Cluster Migration v13 | IT | Application Management | Create | Test Engineer | IT | Test Engineer 1 | 15 | Test planning; Test execution; Quality assurance
Regulatory Program | Regulatory Cluster Migration v13 | IT | Application Management | Create | Solution Architect | IT | Solution Architect 1 | 23 | Architecture design; Technical guidance; Solution review