## Resource Allocations
Program Name | Project Name | Capability Domain | Capability Name | Action | Job Function | Resource Type | Resource Number | Estimated Man/Days | Tasks
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Regulatory Compliance | Update | Business Analyst | IT | Business Analyst 1 | 13 | Requirements analysis; Process documentation; Stakeholder management
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Regulatory Compliance | Update | Software Engineer | IT | Software Engineer 1 | 12 | Technical implementation; Code development; Unit testing
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Regulatory Compliance | Update | Test Engineer | IT | Test Engineer 1 | 9 | Test planning; Test execution; Quality assurance
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Regulatory Compliance | Update | Solution Architect | IT | Solution Architect 1 | 12 | Architecture design; Technical guidance; Solution review
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Risk Management | Update | Business Analyst | IT | Business Analyst 1 | 12 | Requirements analysis; Process documentation; Stakeholder management
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Risk Management | Update | Software Engineer | IT | Software Engineer 1 | 16 | Technical implementation; Code development; Unit testing
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Risk Management | Update | Test Engineer | IT | Test Engineer 1 | 15 | Test planning; Test execution; Quality assurance
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Document Management | Delete | Business Analyst | IT | Business Analyst 1 | 4 | Requirements analysis; Process documentation; Stakeholder management
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Document Management | Delete | Product Owner | IT | Product Owner 1 | 5 | Backlog management; Feature prioritization; Value assessment
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Document Management | Delete | Software Engineer | IT | Software Engineer 1 | 8 | Technical implementation; Code development; Unit testing
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Document Management | Delete | Test Engineer | IT | Test Engineer 1 | 5 | Test planning; Test execution; Quality assurance
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Document Management | Delete | Solution Architect | IT | Solution Architect 1 | 8 | Architecture design; Technical guidance; Solution review
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Wealth Management | Create | Business Analyst | IT | Business Analyst 1 | 29 | Requirements analysis; Process documentation; Stakeholder management
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Wealth Management | Create | Software Engineer | IT | Software Engineer 1 | 28 | Technical implementation; Code development; Unit testing
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Wealth Management | Create | Test Engineer | IT | Test Engineer 1 | 25 | Test planning; Test execution; Quality assurance
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Wealth Management | Create | Solution Architect | IT | Solution Architect 1 | 19 | Architecture design; Technical guidance; Solution review
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Customer Onboarding | Delete | Business Analyst | IT | Business Analyst 1 | 6 | Requirements analysis; Process documentation; Stakeholder management
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Collateral Management | Update | Business Analyst | IT | Business Analyst 1 | 11 | Requirements analysis; Process documentation; Stakeholder management
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Collateral Management | Update | Software Engineer | IT | Software Engineer 1 | 21 | Technical implementation; Code development; Unit testing
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Collateral Management | Update | Test Engineer | IT | Test Engineer 1 | 10 | Test planning; Test execution; Quality assurance
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Collateral Management | Update | Solution Architect | IT | Solution Architect 1 | 17 | Architecture design; Technical guidance; Solution review
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Payment Execution | Delete | Business Analyst | IT | Business Analyst 1 | 8 | Requirements analysis; Process documentation; Stakeholder management
Regulatory Program | Regulatory Cluster Migration v2 | BUSINESS | Payment Execution | Delete | Software Engineer | IT | Software Engineer 1 | 8 | Technical implementation; Code development; Unit testing